## Project Timeline
PROJECT TIMELINE TECH TRACK | [9 empty] | This is a modified form of a Gantt chart which focuses on creating a project schedule that is broken down into stages.
PROJECT TITLE |  | Combined GPS and Intensity-based Alignment of Laser Devices |  | COMPANY NAME | [6 empty] | Track Tech
PROJECT MANAGER |  | Dawson Burgess |  | LAST UPDATE DATE | [6 empty] | 2024-03-05
PHASE |  |  | DETAILS | Semester 1 | [13 empty] | Semester 1 | [12 empty] | Semester 2 | [14 empty] | Semester 2
|  |  |  | August |  |  |  |  | September |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  |  | December |  |  | January |  |  |  |  | Febuary |  |  |  |  | March |  |  |  |  | April |  |  |  |  | May
| Project Phase: |  |  |  | 7 | 14 | 21 | 28 | 4 | 8 | 11 | 15 | 18 | 22 | 25 | 29 | 30 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 30 | 4 | 11 | 18 | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 16 |  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 1 | 6 | 13
1 | Project Conception |  | - Project Bids | [50 empty] | PROJECT END
- Meeting team and instructor
- Meeting with client
- Plan and document Initiation
2 | Project Definition and Planning |  | - Product Requirements document + Value Proposition
- Scope and Goal Setting
- Budget and Gantt Chart
- Review of prototype and existing code base
- Work Breakdown
3 | Project Launch & Execution |  | - Testing Existing Code and Prototype
- Code prototyping / design
-Order then Installing and testing GPS modules
- Coding
- Code Refinement
4 | Project Performance & Control |  | - Code Deployment testing on protoype
- Client Feedback
- Code Testing and big fixes and additions
- Packaging
5 | Project Close |  | - Project Punchlist
- Postmortem
- Expo Preperation
- Final Report

## Task BreakDown
Phase of Project | Task Name | LAST UPDATED: 10/3/23 DB
1. Meeting team and instructor | Initial Meeting with team | Establish Needs of team | Establish comminication standards
1. Meeting with client | Have First meeting with client | Establish Needs and wants of client | Establish Line of Comminication with client and team
1. Plan and Document initialization | Create Budget document | Create Gannt / timeline document | Creat product requirement documents
2. Product Requirements document + Value Proposition | Establish list of product requirements from list of needs and wants | Developing a value proposition | Refine PRD document and finalize
2. Scope and Goal Setting | Establishing the scope of what our project is | Setting goals for over all project and desired outcomes
2. Budget and Gantt Chart | Define parts to be purchased for project requirements | Set budget for project | Develop project task breakdown | Finish Gantt and project task breakdown
2. Review of existing code base, acquiring previous prototype | Get existing code from previous project, establish new repository | get existing prototype from previous project | Review code and understand how it works
2. Work Breakdown Schedule | Develop a more refined work breakdown after evaluation of previous work on the project
3. Testing/Examining Existing Code and Prototype | Layout a specific code schedule and task list | Run tests virtually to understand how code works | Run tests on prototype test harness with varrying conditions
3. Code Prototyping | Determine functions and needed additions to code for project success | Prototype functions to be implemented
3. Installing and testing GPS modules | Installing GPS module to each prototype unit | Testing GPS and arduino board communication | Seeing what data we can work with for alignment
3. Coding Design | Design Functions to get position from GPS module | Design Functions to get desired position | Design Functions to make large scale rotations on prototypes | Design Functions to switch from large scale adjustments to exisitng small scale adjustment algorithm
3. Code Implementation | Coding all functions the team designed | Integrating our code into existing source code | Making changes to existing code
4. Code Deployment testing on protoype | Deploy Code on Prototype | Testing Via PVD requirements | Design code to work with the new optical sensor
4. Client Feedback | Review progress and prototypes with client | Discuss any additions or changes desired by client | x
4. Code Testing, bug fixes and additions | Run tests on code and prototype from different alignment requirements | Fix any bugs or strange behaviour | Applying and additions or changes per client feedback
4. Packaging | Making changes for modularity | Establish standard packaging and build
5. Project Punchlist / Finishing touches | Team Portfolio | SnapShot #3 | Last minute adjustments | Sourcing and editing final documents
5. Postmortem | DVP and Report | Poster
5. Design Expo | Presentation / Poster | Preperation / Rehearsal
5. Final reports | Develop final report | Finish Report | Submit final requirements and reports
complete
incomplete